## Project Procurement Management
https://taskford.com/en
Project Development Plan Template
1. Project Overview
| Project Title | Website Redesign for Acme Corp
| Project Manager | Jane Doe
| Stakeholders | Marketing Team, IT Team, Acme Corp Executive Board
| Objectives | Redesign the corporate website to improve user experience, increase conversion rates by 20%, and ensure mobile responsiveness
| Deliverables | New website design mockups, fully functional website, updated content, QA report
2. Risk Assessment
| dentified Risk | Likelihood (Low/Medium/High) | Impact (Low/Medium/High) | Risk Category | Mitigation Strategy
| Delay in content delivery from Marketing | Medium | High | Schedule | Set earlier internal deadlines; provide clear content requirements; assign backup content contributors
| Technical issues during website migration | Medium | High | Technical | Conduct migration tests on staging environment; have IT team ready for rollback
| Budget overruns due to additional features | Low | Medium | Financial | Approve all new features through change control; maintain 10% contingency budget
| Unclear stakeholder requirements | High | Medium | Scope | Hold detailed kickoff meetings; document requirements; confirm sign-off before design starts
| Third-party plugin incompatibility | Low | High | Technical | Test all plugins in development environment; keep backup solutions ready
3. Resource Allocation
| Resource | Role | Assigned Tasks | Notes
| Jane Doe | Project Manager | Oversee project execution, risk monitoring | Full-time
| IT Team | Developer | Website coding, testing, deployment | 3 Developers, 1 QA
| Marketing Team | Content & Design | Provide updated content, design mockups | 2 Designers, 1 Copywriter
| External Vendor | Plugin Integration | Assist with third-party plugin setup | Contract-based
Budget Allocation
Total Budget: $50,000
Development & Testing: $30,000
Design & Content: $15,000
Contingency: $5,000
Timeline
Kickoff: September 1
Design Approval: September 15
Development: September 16 – October 15
Testing & QA: October 16 – October 25
Launch: October 30
4. Risk Mitigation Strategies
| Risk | Strategy
| Delay in content delivery | Set deadlines 1 week earlier; assign backup content contributors
| Technical issues during migration | Perform staging tests; prepare rollback plan
| Budget overruns | Maintain contingency; approve new features only through change control
| Unclear stakeholder requirements | Conduct detailed requirements meeting; document & get sign-off
| Plugin incompatibility | Test plugins in development; prepare alternatives
5. Monitoring and Control
| Task | Responsible | Frequency | Notes
| Risk Review Meeting | Project Manager | Weekly | Update risk register and mitigation strategies
| Status Report | Project Manager | Bi-weekly | Share progress with stakeholders
| QA Testing | IT Team | End of Development | Ensure all functionalities meet requirements
| Stakeholder Review | Marketing & Executive Team | After Key Milestones | Confirm deliverables align with objectives